COMMUNITY PLAN TO PREVENT AND END HOMELESSNESS IN DANE COUNTY, WISCONSIN

Dane County Homeless Services Consortium

2013 Results

Vision Statement

All households in Dane County should have the opportunity to secure and maintain safe, stable affordable housing.

Guiding Principles

Everyone deserves an equal opportunity to housing free of discrimination.

The Community will continue to explore creative solutions to ending homelessness beyond those objectives highlighted in the Community Plan.

There has to be a shared ownership and responsibility for preventing and ending homelessness across all Dane county groups including, but not limited to, business, faith communities, funders, government, homeless and formerly homeless individuals, and social service providers.

Consumers, those individuals who have been helped by services provided, have an integral role in the design of solutions to prevent and end homelessness.

Community volunteers are recognized as an essential part of preventing and ending homelessness.

The Homeless Services Consortium is a partnership of agencies, funders, advocates and formerly homeless persons and its success at preventing and ending homelessness is dependent on a commitment to the strategies and results in this plan.

Education and Advocacy

The following chart specifically identifies the goals, objectives and strategies that, if fully implemented, would lead us toward the elimination of homelessness.  The Homeless Services Consortium believes that, in order to achieve the following goals, we need to communicate with the public about the impact homelessness has on the greater community and about the necessity of solutions coming from more than non-profit agencies and faith communities.  The Homeless Services Consortium reaffirms our commitment to educate the general public about the presence of homeless families, single adults and youth in Dane County, and to advocate for resources that further our goal of ending homelessness locally and statewide.

| GOALS | OBJECTIVES | STRATEGIES | ANTICIPATED RESULTS | RESPONSIBILITY | RESULTS |
| --- | --- | --- | --- | --- | --- |
| A. Provide support services for homeless households and households at risk of homelessness to enable them to access and maintain stable housing. | 1. Increase the availability of effective case management services. | a. Increase the number of case management staff available to provide support services. | By 2010, the number of homeless families receiving case management services will increase by 50 families over 2005 levels. Continue annual increases to accommodate the need. Source: United Way | Homeless Services Consortium (HSC) agencies, United Way of Dane County | 2005: 1,653 families received case management services. 2010: 1,980 families 2011: 2,111 families 2012: 2,028 families 2013: 2,330 families |
|  |  | b. Improve the effectiveness of case management services through the availability of training and education on best practices and the commitment to purchase such training and education. | By 2011, 80% of households receiving case management through Homeless Services Consortium (HSC) agencies will maintain stable housing at the 6 month mark and 75% will maintain stable housing at the 12 month mark. Source: City of Madison Community Development Office, United Way Dane County (UWDC) |  | 2006 - 2011: United Way held 13 case management trainings with a total of 1,296 participants. 2012 – United Way held 1training with 75 attendees. 2013: United Way held 2 trainings, with 150 attendees 2010: HSC agencies reported between 74%-100% of clients maintained housing at 6 months and 72%-90% of clients maintained housing at 12 months. 2011: HSC agencies reported between 69%-84% of clients maintained housing at 6 months and 64%-84% of clients maintained housing at 12 months. 2012: HSC agencies reported between 61%-100% of clients maintained housing at 6 months and 65%-84% of clients maintained housing at 12 months. |
|  |  |  | By 2013, explore the creation of a case manager handbook to assist new employees in HSC agencies that serve homeless and those at risk of homelessness. Source: UWDC | United Way of Dane County HSC Agencies | 2013: HSC agencies reported an average of 91% of clients maintained housing at 6 months and 85% maintained housing at 12 months. |
| A. Provide support services for homeless households and households at risk of homelessness to enable them to access and maintain stable housing. (continued) |  | c. Recognize the importance of the roles all persons who come in contact with homeless persons play and commit to providing training and support. | Provide at least one (1) training program available to support persons on homeless issues and strategies to ensure success in housing. Source: UWDC | United Way of Dane County HSC agencies | 2011: United Way held 15 trainings geared to persons other than case managers on assisting homeless households 2012 & 2013: No trainings were held. |
|  | 2. Increase the number of households who retain stable housing who might otherwise become homeless. | a. Increase the availability of financial assistance to prevent homelessness for households at risk. | Increase the number of households (over the 2011 level) who avoided homelessness as a result of receiving short-term financial assistance such as payment of rent or utilities in arrears. Source: City of Madison, UWDC, HSC Agencies | Federal, state and local government HSC agencies | 2011: 1,059 households receiving financial assistance avoided homelessness. 2012: 2,065 households 2013: 1,899 households |
|  | 3. Increase mainstream resources and benefits to households so that they are able to afford the cost of housing. | a. Increase the number of households approved for SSI/SSDI and other mainstream benefits and shorten the length of time between application and approval of SSI/SSDI benefits by advocating for institutional change and improving agencies’ knowledge of the application process. | 10% annual increase in the number of households who receive SSI/SSDI benefits. Source: Social Security Administration, Dane County Human Services 10% annual increase in the number of households who receive entitlement programs through Dane County Human Services. Source: Dane County Human Services | Federal, state and local government HSC agencies DCHS Social Security Administration | 2005 – 2010: 232 SSI/SSDI cases approved. 2011: 38 SSI/SSDI cases approved through County’s contract with ERI 2012: 22 SSI/SSDI cases approved 2013: 46 SSI/SSDI cases approved 2005: 19,274 households received mainstream resources. 2010: 38,653 households 2011: 25,789 households 2012: 38,111 households 2013: 38,556 households |
| A. Provide support services for homeless households and households at risk of homelessness to enable them to access and maintain stable housing. (continued) |  | b. Maximize the available financial resources for housing by extending access to safety-net supports such as food, clothing, EITC. | Increased use of available free foods (TEFAP); access to food pantries as often as needed and food pantry shift to customer-selected food; access to tax preparation assistance to claim Earned Income Tax Credit. Source: UWDC | UWDC Hunger Prevention Council, Dane County Food Pantry Network, HSC agencies | 2005: 4.6 million pounds of food distributed. 2010: 6.7 million pounds 2011: 7 million pounds 2012: 7.4 million pounds 2013: 7.6 million pounds |
|  | 4. Advocate for employment resources including basic education. | a. Improve connections between those persons seeking employment and employers. Ensure a level of comprehensive supportive services and mentors to improve chances of success in obtaining and maintaining employment. | Pilot program(s) will be initiated that will recruit employers and potential employees from HSC agencies to match those in need of employment with available jobs. Source: HSC agencies | Local business community HSC agencies | 2007: DCHS contracts with EATA to provide employment services to homeless persons. 2008 – 2010: 370 participants found employment. Contract ended December 2010. 2013: HSC programs employed 66 homeless individuals through Porchlight Products and Just Bakery (MUM) |
|  | 5. Advocate for basic education resources. | a. Increase the emphasis by HSC agencies on adult basic education opportunities, including GED and HSED. b. Collaborate with the homeless liaisons in area school districts to insure that homeless school aged children are quickly enrolled in school and afforded all protections under the McKinney-Vento mandates. | Increased number (over 2006 level) of Dane County residents with high school diplomas or equivalency. Source: U.S. Census Bureau Homeless school-aged children will continue to be quickly enrolled in school, in accordance with McKinney-Vento mandates. | Federal, state and local government Private foundations / funders DPI/ MMSD/ other County public school districts HSC agencies MMSD Transitional Education Program (TEP), MCPASD, and homeless liaisons in other Dane County school districts | 2006: 5.6% of workforce has less than a high school diploma or equivalent. 2010: 5.3% of workforce has less than a high school diploma or equivalent 2011: 5.6% 2013: 5% 2011: 1,001 school-age homeless children received services 2012: 1,709 school-age homeless children received services 2013: 1,287 school-age homeless children received services |
| A. Provide support services for homeless households and households at risk of homelessness to enable them to access and maintain stable housing. (continued) | 6. Advocate for mental health resources and alcohol and other drug abuse treatment. Advocate for services to treat those with dual diagnoses. | a. Increase the on-going support services available to people with mental illnesses including those with a dual diagnosis. | Annual increase (over the 2006 level) of Community Support Program (CSP) slots providing on-going services to clients in their homes. Source: WI DCF | Federal, state and local government Mental Health Center of Dane County HSC agencies | 2006: 562 CSP slots funded 2010: 559 CSP slots funded 2011: 559 CSP slots funded 2012: 554 CSP slots funded 2013: 554 CSP slots funded |
|  |  |  | Increase (over the 2006 level) the number of supportive living units serving persons with persistent mental illness who require a higher level of support to maintain stable housing Source: City of Madison, HSC Agencies, DCHS | Federal, state and local government HSC agencies | 2006: 174 units 2010: 248 units 2011: 263 units 2012: 311 units 2013: 326 Units |
|  |  | b. Increase the availability of out-patient treatment for persons with alcohol and other drug abuse (AODA) issues including those with a dual diagnosis. | The number of out-patient treatment slots will increase (over the 2006 level), with comparable increases in each five year period after. Source: HSC Agencies, DCHS | Federal, state, and local government Private foundations / funders HSC agencies | 2006: 526 day treatment slots 2010: 610 day treatment slots 2011: 589 day treatment slots 2012: 600 day treatment slots 2013: 600 day treatment slots |
|  |  | c. Increase the availability of residential treatment beds for persons with mental illness, AODA issues and co-occurring substance abuse and mental health needs. | The number of residential treatment beds will increase (over 2006 level), with comparable increases in each five year period after. Source: HSC Agencies, Dane County Human Services The number of residential treatment beds serving persons with both mental illness and AODA issues will increase (over 2011 level). Source: HSC Agencies, Dane County Human Services | Federal, state, and local government Private foundations / funders HSC agencies | 2006: 84 residential treatment beds for persons with AODA issues. 2010: 70 residential treatment beds 2011: 58 residential treatment beds 2012: 47 residential treatment beds 2013: 47 residential treatment beds |
| A. Provide support services for homeless households and households at risk of homelessness to enable them to access and maintain stable housing. (continued) |  | d. Provide support services to women who need AODA treatment to either retain or regain custody of their children. Also provide support for the children of parents with AODA issues. | Increase number (over 2006 levels) of women receiving AODA treatment who retain or regain custody of their children. Source: ARC Community Services, DCHS, UWDC | Federal, state and local government Private foundations / funders ARC Community Services HSC agencies | 2006: 83 women retained or regained custody of their children. 2010: 71 women retained or regained custody of their children. 2011: 2012: 2013: |
|  |  | e. Increase AODA treatment services to those in jail, and provide community aftercare for those being released from jail. | Increased budget for providing AODA treatment for those in jail. Source: DCHS | Federal, State and local government HSC agencies | 2006: $2,245,148 in Dane Co. Jail Diversion funding. 2010: $2,587,363 2011: $2,689,393 2012: $2,733,617 2013: $2,899,655 |
|  | 7. Advocate for child care resources | a. Support an increase in the availability and affordability of quality child care to low-income households. | Increase the number (over 2011 level) of households receiving subsidized child care slots funded by the state and funded by the City.. Source: DCHS, City of Madison, Community Coordinated Child Care, Inc. (4C’s) | Federal, state and local government Private foundations / funders HSC agencies and advocates Community Coordinated Child Care Private sector | 2011: 3,990 families received subsidized child care assistance from the state. 2012: 3,713 families 2013: 3,288 families 2010: 108 families received subsidized child care assistance from the City of Madison. 2011: 92 families 2012: 98 families 2013: 93 families |
|  | 8. Advocate for transportation resources. | a. Support the access to a variety of transportation options available to low-income households enabling them to access jobs and child care. | Increase the ability of households to obtain low or no-cost transportation options. Source: HSC agencies | Federal, state and local government Private foundations / funders HSC agencies Private sector | 2007: 599 employment-related rides through Transit for Jobs. 2010: 14,458 employment-related rides through JobRide and YWTransit. 2011: 17,130 employment-related rides 2012: 51,749 employment-related rides 2013: 58,734 employment-related rides |
| A. Provide support services for homeless households and households at risk of homelessness to enable them to access and maintain stable housing. (continued) | 9. Advocate for medical and dental services for homeless persons. | a. Support access to medical services through a variety of entry points with the goal of connecting households with a “medical home”. b. Support access to dental services to ensure that adults and children receive services as needed. | Increase the number (over the 2011 level) of homeless persons who are provided access to medical services through the emergency shelter system and other access points. Source: Meriter HEALTH, GHC Increase the number (over the 2011 level) of homeless persons who are provided dental services through the emergency shelter system and other access points. Source: The Salvation Army, AIDS Network | HSC Agencies, The Salvation Army Meriter HEALTH HUT Group Health Cooperative AIDS Network Private Sector | 2009:37 patients received medical services through the HEALTH Hut. 2010: 226 patients 2011: 413 patients 2012: 244 patients 2013: 148 patients 2011: 24 homeless families received medical services through Group Health Cooperative. 2012: 24 homeless families 2013: 59 homeless families 2011: 380 homeless individuals who received dental services through The Salvation Army dental clinic; 140 persons receiving dental services through AIDS Network clinic. 2012: 665 individuals – The Salvation Army dental clinic; 163 individuals - AIDS Network clinic. 2013: 831 individuals – The Salvation Army; |
|  | 10. Advocate for resources for re-integrating offenders. | a. Support those persons released from prison who are re-entering the community and need assistance navigating the often inaccessible housing and services market. | Increase the number (over the 2006 level) of former prisoners linked with housing and services needed to successfully re-enter the community. Create/maintain partnerships with HSC agencies and the Department of Corrections to minimize barriers to finding appropriate housing in Dane County. Source: HSC, DOC | Federal, state and local governments WI Department of Corrections Madison-area Urban Ministry Porchlight, SVdP Private Sector | 2006: MUM’s Journey Home program assisted 80 former prisoners with employment. 2010: MUM assisted 38 with employment and 36 with housing. 2011: MUM assisted 78 with employment and 117 with housing 2012: MUM assisted 58 with employment and 49 with housing 2013: MUM assisted 44 with employment and 14 with housing 2006: DOC contracts with HSC agencies for beds for homeless ex-offenders – Porchlight (4), SVdP (3). 2010 - 2013: Porchlight (2), SVdP (3) |
| A. Provide support services for homeless households and households at risk of homelessness to enable them to access and maintain stable housing. (continued) | 11. Provide financial education to help households better manage their resources. | a. Improve access to financial education and counseling services through new and existing programs. | The number of households who complete financial literacy and tenant education classes offered by HSC agencies will increase annually (over 2006 level). Source: HSC agencies | UWDC, Private foundations / funders HSC agencies Private sector | 2006: 953 households served. 2010: 864 households served. 2011: 195 households served 2012: 624 households served. 2013: 243 2nd Chance Tenant Workshops |
|  |  | b. Increase training of financial literacy skills in public schools. | The number of youth who complete financial literacy education classes offered by HSC agencies and others will increase annually (over 2006 level). Source: HSC agencies | YWCA HSC agencies Private sector | 2006: 129 MMSD youth served 2010: 358 MMSD youth served 2011: 186 MMSD youth served 2012: 116 MMSD youth served 2013: 55 MMSD youth served |
|  | 12. Build on efforts to improve relationships between landlords, tenants and non-profit agencies. | a. Decrease the number of evictions by providing access to landlord/tenant mediation, financial assistance to pay a portion of back rent and protective payee services when appropriate. | Annually decrease the number of Dane County evictions filed from 2006 levels. Source: Dane County Clerk of Court Increase the number of active protective payees (over the 2011 level) who are trained and available to work with households who express an interest. Source: DCHS | Tenant Resource Center CACSCW Porchlight HSC agencies DCHS Property owners/landlords | 2006: 3,062 evictions filed 2010: 3,046 evictions filed 2011: 3,062 evictions filed 2012: 2,836 evictions filed 2013: 2,386 evictions filed 2011: 554 households received assistance through a protective payee program 2012: 647 households 2013: 655 households |
|  | 13. Protect the legal rights of tenants to ensure that all are treated without discrimination and within the boundaries of the law. | a. Increase legal advocacy services to tenants so that homelessness is prevented via legal representation when appropriate. | The number of households who received legal assistance will increase annually (over 2006 level). Source: HSC agencies | Legal Action of WI, TRC, HSC agencies, Neighborhood Law Project Funders, Advocates and Tenants | 2006: 51 households avoided eviction through legal advocacy efforts. 2010: 78 households. 2011: 52 households 2012: 38 households. In addition, 682 households served through housing mediations by Tenant Resource Center 2013: 31 households – legal advocacy; 385 households – housing mediation |
| B. Help homeless households by providing a short-term safety net with continuous support services with the goal of moving to stable housing as quickly as possible. | 1. Provide safe shelter beds for homeless families with children and single adults until such time that other more appropriate housing alternatives are available. Provide a safe environment for transgender individuals, young adults aged 18 to 24, and others who might have difficulty in traditional shelter settings. | a. The HSC will review the continuing need for shelter and overflow beds and explore other effective shelter alternatives based on solid data. | Annually the HSC will review available data on shelter use and the perceived unmet need and make recommendations to the appropriate organizations regarding future policy and funding decisions. The HSC, through the Shelter Providers Committee, will address solutions to sheltering persons in a safe, non-judgmental environment. Source: HSC agencies | HSC shelter provider agencies, funders and advocates Private foundations/ funders | 2006: 3,207 individuals turned away without shelter 2010: 1,410 individuals turned away without shelter 2011: 2,003 individuals turned away without shelter 2012: 1,654 individuals turned away without shelter 2013: 1,243 individuals turned away without shelter |
|  | 2. Provide short term and transitional housing options for unaccompanied youth and unaccompanied parenting youth. | a. The HSC will advocate for resources to create housing options for unaccompanied youth and parenting youth. | Maintain the number of existing short-term options (over the 2006 level) and increase the availability of transitional housing options (create 6 units by 2016) for unaccompanied youth and parenting youth. Source: HSC agencies | Federal, state and local government Private foundations/ funders Youth Services of Southern Wisconsin (YSOSW)– Briarpatch HSC agencies | 2006: 8 volunteer host homes licensed through YSOSW. 2010: 7 volunteer host homes. 2011: 5 volunteer host homes 2012: 4 volunteer host homes 2013: 4 volunteer host homes 2011 & 2012 & 2013: 0 transitional housing units available to serve unaccompanied youth and parenting youth. |
|  | 3. Ensure safe housing alternatives with on-going supportive services for survivors of sexual assault and domestic abuse. | a. Support the efforts of HSC agencies in their activities to provide services and safe housing for survivors of all types of domestic violence and sexual assault. | Safe environment for persons who have suffered from the effects of violence in their homes and community. Source: HSC Agencies, | Federal, state and local government Private foundations/ funders Domestic Abuse Intervention Services YSOSW-Briarpatch HSC agencies City of Madison Community Development Office Private Sector | 2006: 15% of homeless households indicated “violence or threat of violence as primary reason for seeking shelter 2010: 21% 2011: 15% 2012: 25% 2013: 14% 2011-2013: safe transitional housing for 3 singles and 6 families |
| B. Help homeless households by providing a short-term safety net with continuous support services with the goal of moving to stable housing as quickly as possible. (continued). | 4. Support persons released from hospitals to help them access housing and other services | a. Create new partnerships between the HSC agencies, funders and local hospitals and medical facilities to develop a process to determine appropriate housing prior to discharge and explore the local need for a short-term housing option to serve persons who are released from hospitals who are physically unable to work or who are going through extensive out-patient treatment and who would otherwise be homeless | Increased availability (over 2006 levels) of safety net housing for individuals whose temporary medical conditions would otherwise result in their homelessness. Source: HSC Agencies, City CDBG Office | The Salvation Army HSC Agencies | 2006: 22 individuals with medical needs served with vouchers. 2010: 23 individuals. 2011: 31 individuals 2012: 19 individuals 2013: 27 individuals |
|  | 5. Provide and expand on access for homeless households to store personal belongings and to access transportation services, voice mail, internet, showers and meals during the daytime hours. | a. Support the expansion of programs that supply personal storage space and daytime access to transportation, voice mail, internet, showers and meals. Expand the locations where these services are available and explore the unmet need for additional services. | Increased consumer satisfaction with the storage and daytime services available to them in order to access employment and stable housing. Source: Customer Satisfaction Surveys, 2006 Needs Assessment Survey | Porchlight Madison Public Library HSC agencies Private foundations/ funders Private Sector | 2006: Lost existing service with closing of Pres House. 2010: Service offered at SVdP; 72 individuals used storage facility. 2011: 180 individuals used SVdP storage facility. 2012: 182 individuals used SVdP storage facility. 2013: 185 individuals used SVdP |
|  | 6. Provide effective street-level outreach to increase the access to housing and services by homeless individuals. | a. Provide year-round outreach services to better connect single adults living in uninhabitable places to needed services. | Annually 30 single adults will move from the streets to residential treatment or supportive housing. Source: HSC agencies data, | Federal, state and local government Private Sector Tellurian UCAN Porchlight YSOSW-Briarpatch | 2006: 69 individuals moved from streets into housing. 2010: 59 individuals 2011: 64 individuals. 2012: 49 individuals 2013: 40 individuals |
| B. Help homeless households by providing a short-term safety net with continuous support services with the goal of moving to stable housing as quickly as possible. (continued) | 7. Provide effective outreach to families with children who are living in unsafe, uninhabitable places to increase access to housing and services. | a. Provide year-round outreach to better connect families with children who are living in unsafe and uninhabitable places to needed services | School districts in Dane County, through the Homeless Liaisons, will successfully connect homeless families with children to needed services and housing options. Source: DPI | Federal, state and local government and school districts, HSC family shelter providers | 2011: 1,001 families with children who received services through Dane County public schools. 2012: 1,709 families with children received services. 2013: |
|  | 8. Provide effective outreach to unaccompanied youth living in unsafe or in uninhabitable places to increase access to housing and services. | a. Provide year-round outreach to better connect unaccompanied youth living in unsafe places to needed services, | The number of staff hours devoted to providing outreach services to unaccompanied youth will increase (over 2006 level). Source: YSOSW | Federal, state and local government YSOSW-Briarpatch | 2011: 21 unaccompanied youth moved from homelessness to safe housing. 2012: 21 unaccompanied youth 2013 11 unaccompanied youth |
| C. Provide an adequate inventory of affordable housing units for low-income households, whether by creating new units or making existing units affordable | 1. Grow local “Housing First” model to serve the needs of homeless families, single adults, and young adults aged 18 to 24. | a. Place homeless individuals and families in permanent housing as quickly as possible, providing intensive home-based case management and stabilizing support services. | Annually increase (over the 2008 level) the number of permanent units available to homeless families, single adults and young adults aged 18 to 24 that are part of housing first programs. Source: UWDC | Federal, state and local government UWDC HSC agencies | 2006: 16 units for families; 2 units for single adults 2010: 131 units for families; 19 units for single adults 2011: 152 units for families; 19 units for single adults 2012: 152 units for families; 12 units for single adults 2013: 54 units for families; 13 units for single adults Note: Housing First broadly defined by funders and providers. |
|  | 2. Provide a variety of housing units that are affordable for low-income single adults and families with children, and for those with special needs such as mental illness or physical disabilities. | a. Maintain the current number of federally subsidized rental units operated by non-profits and private developers. b. Create incentives for non-profit and for-profit housing developers to construct new affordable housing units. | Maintain or increase the number of federally subsidized rental units in Dane County for low-income households. Source: WI Housing and Economic Development Authority (WHEDA) Support local, state and federal incentives and tools such as a housing trust funds to encourage development of affordable housing. | Federal, state and local government City of Madison and Dane County Community Development Offices Housing in Action Leadership Team Greater Madison Chamber of Commerce Work Force Housing Fund Private Housing Developers | 2006: 7,440 total units 2010: 7,727 total units 2011: 7,904 total units 2012: 8,628 total units 2013: No update to WHEDA list |
| C. Provide an adequate inventory of affordable housing units for low-income households, whether by creating new units or making existing units affordable. (continued) |  | c. Support HSC agencies and other non-profit housing developers who create affordable housing units, coupled with supportive services, for households with issues such as mental illness, AODA, and other physical and mental disabilities. | Increase the number of supportive housing units created (over 2006 level). Source: City of Madison Community Development Office, Dane County Community Development Office | Federal, state and local government WHEDA Private foundations/ funders Goodwill Industries Housing Initiatives Porchlight Society for St. Vincent de Paul Tellurian Movin’ Out HSC agencies | 2006: 254 transitional units; 578 supported permanent units. 2010: 276 transitional units; 668 supported permanent units. 2011: 274 transitional units; 701 supported permanent units. 2012: 276 transitional units; 783 supported permanent units. 2013: 177 transitional units; 606 supported permanent units. Note: Beds not dedicated to homeless residents removed; actual increase in units – 16 |
|  |  | d. Increase the number of existing rental units that are affordable to low-income households by encouraging a variety of models including but not limited to partnerships between non-profit agencies and private partners who subsidize the cost of rent. | Increase the number of housing units per year created by HSC agencies to house homeless households that are financially supported by private community organizations (for example, faith communities) or small pilot projects. Source: HSC | YWCA/The Road Home HSC agencies Faith communities Private sector | 2006: 16 units (Second Chance) 2010: 16 units 2011: 11 units 2012: 8 units 2013: 12 units |
|  |  | e. Increase the number of existing rental units that are affordable to low-income households through the use of Housing Choice vouchers (Section 8), Shelter Plus Care, HOPWA vouchers and locally designed rent subsidy programs by advocating for increases in federal and state funding. | Retain the number of Housing Choice vouchers distributed by the Community Development Authority and the Dane County Housing Authority. Through advocacy, increase the number of Housing Choice vouchers in future federal budgets. Source: CDA,DCHA | Federal government Community Development Authority (CDA) Dane County Housing Authority (DCHA) AIDS Resource Center | 2006: Total 2,614 Housing Choice vouchers 2010: Total 2,736 Housing Choice vouchers 2011: Total 2,701 (2,633 Housing Choice vouchers & 68 HOPWA vouchers) 2012: Total 3,126 (2,804 Housing Choice vouchers, 87 HOPWA, 85 HUD-VASH & 150 Family Unification Program) 2013: No Change |
| C. Provide an adequate inventory of affordable housing units for low-income households, whether by creating new units or making existing units affordable. (continued) |  |  | Annually the HSC will apply for funds that can be used to pay a portion of the household’s rent for a specific period of time, thereby making the rental unit affordable. New sources of funding to increase the number of units will be explored. Source: HSC, City of Madison and Dane County Community Development Offices | Federal, state and local government City of Madison and Dane County Community Development Offices HSC agencies | 2006: 60 short-term subsidies (ESG), 44 long term subsidy (CoC) 2010: 27 short-term subsidies (ESG), 125 long-term subsidies (CoC). 2011: 8 short term subsidies (ESG), 206 long-term subsidies (CoC) 2012: 25 short term subsidies (ESG), 143 long-term subsidies (CoC) 2013: 267 long-term subsidies (CoC+ United Way) |
|  |  |  | Increase the number of Shelter Plus Care slots available to Dane County disabled individuals over the 2006 level. | Federal, state and local government Housing Initiatives HSC agencies | 2006: 110 S+C slots 2010: 106 S+C slots 2011: 104 S+C slots 2012: 104 S+C slots 2013: 104 S+C slots |
|  |  | f. Support full funding of public housing units that, in addition to providing safe scattered-site housing, provide housing counseling and support services to low-income Dane County households. | Increase over the 2006 level the number of public housing units in Dane County available to low-income households. Source: CDA, DCHA | Federal, state and local government Community Development Authority Dane County Housing Authority | 2006: CDA 857 units, DCHA 102 units 2010: No change 2011: 24 fewer units at CDA’s Truax due to construction 2012: CDA 859 units, DCHA 102 units 2013 No Change |
|  |  |  | Increase the number of staff (over 2006 level) dedicated to providing housing counseling to public housing tenants, assisting tenants in maintaining stable housing. Source: CDA, DCHA | Federal, state and local government Community Development Authority Dane County Housing Authority | 2006 - 2011: 2 FTEs dedicated to housing counseling public housing tenants. 2012: 2 FTEs 2013: 2 FTEs |

Created: April 2006;  Plan Reviewed/Updated: June 2011 by the Dane County Homeless Services Consortium